## Gate-Milestone
Work Breakdown Structure - STRX RFE SW
Status for: |  | 2020-07-16
Level | WBS | Task Description | Assigned To | Status | Effort estimation (days) | Notes
1 | 1 | PDA Phase |  |  | 85.5
2 | 1.1 | RFE HW RS review: ~x15: | Team | Done | 15
2 | 1.2 | RFE Cluster RS review | Team | Done | 3
2 | 1.3 | Safety Concept AS/RS/HIS | Sandeep BB | Done | 20 | Part of RS already
2 | 1.4 | RFE SW RS
3 | 1.4.1 | Add Verification RS to RFE SW RS | Artur Burchard | Done | 1
3 | 1.4.2 | Review RFE SW RS wrt RFE HW RS | Team | Done | 2
3 | 1.4.3 | Review RFE SW RS wrt RFE Cluster RS | Artur Burchard | Done | 2
3 | 1.4.4 | Review meeting | Team, Reviewers | Done | 0.5
3 | 1.4.5 | Rework review comments | Team | Done | 1
3 | 1.4.6 | Rework review acceptance meeting | Team, Reviewers | Done | 2
3 | 1.4.7 | Fill in all attributes | Artur Burchard | Done | 2
3 | 1.4.8 | Rationale/Fit Criteria | Team | Done | 4
3 | 1.4.9 | Vertical Links: To SYS RS, RFE RS, Safety RS (HIS), RFE HW RS | Team | Done | 4
2 | 1.5 | RFE SW AS
3 | 1.5.1 | Align with Marthijn de Man | Artur Burchard | Done | 0.5
3 | 1.5.2 | Rework after align | Artur Burchard | Done | 5
3 | 1.5.3 | Review meeting | Team | Done | 0.5
3 | 1.5.4 | Rework review comments | Team | Done | 2
3 | 1.5.5 | Rework review acceptance meeting | Team, Reviewers | Open | 1
2 | 1.6 | Test Specification for RFE SW RS | Biju Ravindran | Done | 5 | Initial version required for PDA
2 | 1.7 | Software Configuration Management Plan | Vinoth Ranee Kumar | Done | 2
2 | 1.8 | Software Quality Management Plan | Rashmi K C | Done | 2
2 | 1.9 | Work Breadown Structure (this document) | Grzegorz Kulik | Done | 2
2 | 1.10 | Project Management Plan (Safety Plan) | Grzegorz Kulik | Done | 4
2 | 1.11 | STRX vs Barracuda, Presentation | Artur Burchard | Open | 2 | Initial version
2 | 1.12 | RFE SW Architecture Presentation | Artur Burchard | Open | 1
2 | 1.13 | Project Timeline / planning for PDA | Sushil Kumar Gupta | Done | 2 | Final for PPA / Initial after PPA
2 | 1.14 | Participate in IP review meeting | Team | Open | 0 | Were we not invited? The meetings did not happen?
1 | 2 | PPA Phase |  |  | 363.75
2 | 2.1 | RFE SW RS
3 | 2.1.1 | Vertical link to Overall SW AS DD DOORS | Team | Open | 2
3 | 2.1.2 | Horizontal link to Test Spec | Team | Open | 2 | How to do this since Test Specs are not in DOORS?
2 | 2.2 | RFE SW AS
3 | 2.2.1 | Port whole doc to Enterprise Architect | Artur Burchard/Sandeep BB | Open | 20
3 | 2.2.2 | Vertical Linking to RFE SW RS | Artur Burchard | Open | 2
3 | 2.2.3 | Horizontal Linking to Test Specs/Code? | Artur Burchard | Open | 2 | Is this needed?
2 | 2.3 | Organize project | Artur Burchard | Open
3 | 2.3.1 | Jira - tickets management (PR, IR, CR) | Vinoth Ranee Kumar | Done | 2
3 | 2.3.2 | CCB Initialization and management | Burkchard Braeuer | Done | 2
3 | 2.3.3 | SCRUM: DevelopmentCycles (Sprints) | Grzegorz Kulik | Open | 2
3 | 2.3.4 | SCRUM: SourceCode | Team | Open | 2
2 | 2.4 | SW Units RS (x 55) |  | Open |  | Initial/Final - 17 Existing IPs, 38 New IPs
3 | 2.4.1 | Study IP Datasheets | Team | Open | 15
3 | 2.4.2 | Create SW Unit RS: New 36 SW Units | Team | Open | 108 | Initial for all Ips: 3 days a Unit
3 | 2.4.3 | Create SW Unit RS: New 2 SW Units | Sandeep BB | Open | 8 | Initial for all Ips: 4 days a Unit
3 | 2.4.4 | Create SW Unit RS: Existing 15 SW Units | Team | Open | 30 | initial for all Ips: 2 days a Unit
3 | 2.4.5 | Create SW Unit RS: Existing 2 SW Units | Sandeep BB | Open | 4 | initial for all Ips: 2 days a Unit
3 | 2.4.6 | Organize Units RS final review | Grzegorz Kulik | Open | 2
3 | 2.4.7 | Units RS final review meeting | Team, Reviewers, Sandeep BB | Open | 13.75 | Estimation 2h a review
3 | 2.4.8 | Vertical Linking to RFE SW RS (x53) | Team | Open | 10.6 | 1.5h per linking
3 | 2.4.9 | Vertical Linking to RFE SW RS (x2) | Sandeep BB | Open | 0.4 | 1.5h per linking
3 | 2.4.10 | Horizontal Linking to SW Units TS (x53) | Team | Open | 10.6 | 1.5h per linking
3 | 2.4.11 | Horizontal Linking to SW Units TS (x2) | Sandeep BB | Open | 0.4 | 1.5h per linking
2 | 2.5 | SW Units TS (x53) | Team | Open | 106 | Unit Test Specifications: 2 days a Unit
2 | 2.6 | SW Units TS (x2) | Sandeep BB | Open | 4 | Unit Test Specifications: 2 days a Unit
2 | 2.7 | Test Specification for RFE SW RS | Biju Ravindran | Open | 10 | Final version for PPA
2 | 2.8 | Project Timeline / planning for PPA | Grzegorz Kulik | Open | 5 | Final version for and after PPA
1 | 3 | RTL Bronze
2 | 3.1 | Set-Up S32DS for RFE-M7 | Kai Gossner | Open | 2
2 | 3.2 | SW Units DD (x55) | Team | Open |  | Detailed design - Initial/Final
3 | 3.2.1 | Create SW Unit DD: New SW Units (x36) | Team | Open | 144 | Initial for IP under construction (e.g. RFE Ips): 4 days a Unit
4 | 3.2.1.1 | Create SW Unit DD: New SW Units (x2) | Sandeep BB | Open | 8 | Initial for IP under construction (e.g. RFE IPs): 4 days a Unit
3 | 3.2.2 | Create SW Unit DD: Existing SW Units (x15) | Team | Open | 30 | Final for infra/exisitng IPs (e.g. Timer): 2 days a Unit
4 | 3.2.2.1 | Create SW Unit DD: Existing SW Units (x2) | Sandeep BB | Open | 4 | Final for infra/exisitng IPs (e.g. Timer): 2 days a Unit
3 | 3.2.3 | Organize Units DD final review | Grzegorz Kulik | Open | 2
3 | 3.2.4 | Units DD final review meeting | Team, Reviewers, Sandeep BB | Open | 13.75 | Estimation 2h a review
3 | 3.2.5 | Vertical Linking to Unit RS (x53)? | Team | Open | 10.6 | 1.5h per linking - is this needed?
3 | 3.2.6 | Horizontal Linking to SW Units TS / Code (x53)? | Team | Open | 10.6 | 1.5h per linking - is this needed?
3 | 3.2.7 | Vertical Linking to Unit RS (x2)? | Sandeep BB | Open | 0.4 | 1.5h per linking - is this needed?
3 | 3.2.8 | Horizontal Linking to SW Units TS / Code (x2)? | Sandeep BB | Open | 0.4 | 1.5h per linking - is this needed?
2 | 3.3 | STRX vs Barracuda, Presentation |  | Open |  | Final version
2 | 3.4 | GUI implementation ready and API generator |  | Open |  | Initial version
2 | 3.5 | Analog Ips
3 | 3.5.1 | Documentation
4 | 3.5.1.1 | Obtain IP register description |  | Open
4 | 3.5.1.2 | Start-up Procedures |  | Open
4 | 3.5.1.3 | Calibration Procedures |  | Open
4 | 3.5.1.4 | BIST Procedures |  | Open
4 | 3.5.1.5 | Work out Register and RFE API delta in compare to Barracuda | Artur Burchard | Open
5 | 3.5.1.5.1 | Check Liang slides | Artur Burchard | Open
5 | 3.5.1.5.2 | xls register comparison (vs Barracuda) | Artur Burchard | Open
5 | 3.5.1.5.3 | RFE API comparison (vs Barracuda) | Artur Burchard | Open
2 | 3.6 | SW Units RS (x55) |  |  |  | Updated
3 | 3.6.1 | Study IP Datasheets | Team | Open
3 | 3.6.2 | Update SW Unit RS: New 38 SW Units | Team | Open |  | Initial for IP under construction (e.g. RFE IPs) Estimation: 4 days a Unit
3 | 3.6.3 | Update SW Unit RS: Existing 17 SW Units | Team | Open |  | Final for infra/exisitng IPs (e.g. Timer) Estimation: 2 days a Unit
3 | 3.6.4 | Organize Unit RS final review | Grzegorz Kulik | Open
3 | 3.6.5 | Unit RS final review meeting | Team, Reviewers | Done
3 | 3.6.6 | Vertical Linking to RFE SW RS | Team | Open |  | Initial for IP under construction (e.g. RFE IPs)
3 | 3.6.7 | Horizontal Linking to SW Units TS | Team | Open |  | 1.5h per linking
2 | 3.7 | SW Units DD |  |  |  | Updated Detailed Design for known IP/Components (at bronze all are known):
3 | 3.7.1 | Create SW Unit DD: New SW Units | Team | Open
3 | 3.7.2 | Create SW Unit DD: Existing SW Units | Team | Open
3 | 3.7.3 | Organize Component Detailed Design final review | Grzegorz Kulik | Open |  | Initial for IP under construction (e.g. RFE IPs)
3 | 3.7.4 | Component Detailed Design final review meeting | Team, Reviewers | Open
3 | 3.7.5 | Vertical Linking to Unit RS | Team | Open | 11 | 1.5h per linking is this needed?
3 | 3.7.6 | Horizontal Linking to SW Units TS / Code? | Team | Open | 11 | 1.5h per linking is this needed?
2 | 3.8 | RFE API design |  | Open |  | Initial
2 | 3.9 | Test Specification for RFE SW RS | Biju Ravindran | Open |  | Updated
2 | 3.10 | SW Units TS (x55) |  | Open |  | Initial, Test Specification
2 | 3.11 | Memory Estimation |  | Open |  | Updated
2 | 3.12 | Performance Estimation |  | Open |  | Initial
2 | 3.13 | RFE Simulation Model (Verilator) |  | Open |  | Initial
2 | 3.14 | Product Implementation |  | Open |  | Initial
2 | 3.15 | Validation Implementation |  | Open |  | Initial
2 | 3.16 | DFT Implementation |  | Open |  | Initial
2 | 3.17 | Test implementation |  | Open |  | Initial
2 | 3.18 | Testing |  | Open
2 | 3.19 | Release: Verification Release |  | Open
1 | 4 | RTL Silver
2 | 4.1 | SW Units RS (x55) |  |  |  | Final
3 | 4.1.1 | Study IP Datasheets | Team | Open
3 | 4.1.2 | Update SW Unit RS: New 38 SW Units | Team | Open |  | Final for all Estimation: 4 days a Unit
3 | 4.1.3 | Update SW Unit RS: Existing 17 SW Units | Team | Open |  | Final for all Estimation: 2 days a Unit
3 | 4.1.4 | Organize Unit RS final review | Grzegorz Kulik | Open
3 | 4.1.5 | Unit RS final review meeting | Team, Reviewers | Done
3 | 4.1.6 | Vertical Linking to RFE SW RS | Team | Open |  | Initial for IP under construction (e.g. RFE IPs)
3 | 4.1.7 | Horizontal Linking to SW Units TS | Team | Open |  | 1.5h per linking
2 | 4.2 | First GUI implementation ready and API generator |  | Open |  | Improved/updated version
2 | 4.3 | Detailed Design for known IP/Components |  |  |  | Final
3 | 4.3.1 | Organize Component Detailed Design final review | Grzegorz Kulik | Open |  | Initial for IP under construction (e.g. RFE IPs)
3 | 4.3.2 | Component Detailed Design final review meeting | Team, Reviewers | Open
2 | 4.4 | RFE API design: Final |  | Open |  | Final
2 | 4.5 | Test Specification: Final |  | Open |  | Final
3 | 4.5.1 | Test Specification for RFE SW RS | Biju Ravindran | Open |  | Updated
3 | 4.5.2 | Horizontal Linking to RFE SW RS |  | Open
2 | 4.6 | Component Test Specification |  | Open |  | Final
3 | 4.6.1 | SW Units TS (x55) |  | Open |  | Initial, Test Specification
3 | 4.6.2 | Horizontal Linking to Component RS |  | Open
2 | 4.7 | Memory Estimation |  | Open |  | Updated
2 | 4.8 | Performance Estimation |  | Open |  | Updated
2 | 4.9 | RFE Simulation Model (Verilator) |  | Open |  | Final
2 | 4.10 | Product Implementation |  | Open |  | Updated
2 | 4.11 | Validation Implementation |  | Open |  | Updated
2 | 4.12 | DFT Implementation |  | Open |  | Updated
2 | 4.13 | Testing |  | Open
2 | 4.14 | Release |  |  |  | Verification Release
1 | 5 | RTL Gold
2 | 5.1 | Memory Estimation |  |  |  | Updated
2 | 5.2 | Performance Estimation |  |  |  | Updated
2 | 5.3 | Product Implementation |  |  |  | Updated
2 | 5.4 | Validation Implementation |  |  |  | Updated
2 | 5.5 | DFT Implementation |  |  |  | Updated
2 | 5.6 | Test implementation |  |  |  | Updated
2 | 5.7 | Testing
2 | 5.8 | Release |  |  |  | Verification Release
1 | 6 | RTL Freeze
2 | 6.1 | Memory Estimation |  |  |  | Updated
2 | 6.2 | Performance Estimation |  |  |  | Updated
2 | 6.3 | Product Implementation |  |  |  | Updated
2 | 6.4 | Validation Implementation |  |  |  | Updated
2 | 6.5 | DFT Implementation |  |  |  | Updated
2 | 6.6 | Test implementation |  |  |  | Updated
2 | 6.7 | Testing
2 | 6.8 | Release |  |  |  | Verification Release
1 | 7 | Tape-Out
2 | 7.1 | Testing
2 | 7.2 | Memory Estimation |  |  |  | Updated
2 | 7.3 | Performance Estimation |  |  |  | Updated
2 | 7.4 | Product Implementation |  |  |  | Updated
2 | 7.5 | Validation Implementation |  |  |  | Updated
2 | 7.6 | DFT Implementation |  |  |  | Final
2 | 7.7 | Test implementation |  |  |  | Updated
2 | 7.8 | Release: DFT Release
2 | 7.9 | Release |  |  |  | Validation Internal Release
1 | 8 | ES1+ 4 weeks
2 | 8.1 | Validation
2 | 8.2 | Testing
2 | 8.3 | Internal reported issues fixing
2 | 8.4 | Memory Estimation |  |  |  | Final
2 | 8.5 | Performance Estimation |  |  |  | Final
2 | 8.6 | Product Implementation |  |  |  | EAR
2 | 8.7 | Validation Implementation |  |  |  | Updated
2 | 8.8 | Test implementation |  |  |  | Updated
2 | 8.9 | Release |  |  |  | EAR 1.0.0 Release
1 | 9 | Bug Fix Releases
2 | 9.1 | Customer reported issues fixing
2 | 9.2 | Internal reported issues fixing
2 | 9.3 | Validation
2 | 9.4 | Testing
2 | 9.5 | Product Implementation |  |  |  | Bug Fix
2 | 9.6 | Validation Implementation |  |  |  | Updated
2 | 9.7 | Release |  |  |  | Bug Fix Release
1 | 10 | Planned Releases / Maintenance
2 | 10.1 | Customer reported issues fixing
2 | 10.2 | Internal reported issues fixing
2 | 10.3 | Testing
2 | 10.4 | Product Implementation |  |  |  | Bug Fix
2 | 10.5 | Release |  |  |  | Early Access Release (EAR X.X.X)