## Document Information
Risk Register Reference Template
Document Identifier | NXPOMS-999116894-13147
Old System Identifier | NXPOMS-999116894-12544
Document Author(s) | Aamer Shaukat; Nagarajan Periasamy; Jolande Geerts - Van Dalen
Document Owner | Jolande Geerts - Van Dalen
Owning Organization | Product and Technology Enablement
Business Process | Product Creation
Applicable to | NXP BL'S; Technology and Operations
Security Level | Company Internal
Objective | See worksheet "usage Guide"
Instructions to use | See worksheet "usage Guide"
Reference documents | NXPOMS-999116894-3972 Risk Register Collabnet Tracker Records Guidelines
Abbreviations / Definitions | REI - Risk Exposure Index Mitigation Plan - the action to prevent risk before it happens Contingency Plan - the action to cure risk after it happens

## User Guide Risk Register
This usage guide describes how this Risk Register Template is to be used.
Creating Your Risk Register (see below for examples of Risk Categories)
Following the defined risk management process, use this template to record all of the risks associated with the project and subsequently review and manage these risks.
When a Risk occurs, it becomes a issue and the probability should be set to 10. After solving the issue it should be removed from the Risk Register sheet and a copy put into the Cleared risks sheet.
When a risk has passed, and it can no longer occur, it should be removed from the Risk Register sheet and a copy put into the 'Cleared Risks' sheet.
The Risk Register sheet can be sorted by selecting all the risk entries and using the standard Data->Sort menu item.
Updating Risks
Risk and Risk Status are to be updated in the “Risk Register Form” worksheet by regularly updating probability or impact values
Using The Risk Exposure Indicator (using the Risk Trend is optional)
Once an initial project Risk meeting has been held, and all of the Risks have been scored, the Risk Exposure Indicator shows the number of Risks associated with a particular probability and impact. REI color formatting: Red >40, Green <20, Yellow 20-40 and Probablity more than 4.
In worksheet "Risk Trend": the "#risks per zone"-tabe counts # of Red or Yellow or Green risks item - based on REI in "Risk Register Form" - when new risk are created or status is updated.
In worksheet "Risk Trend": Copy these values from the "risks per zone"-table into the table above (rows 7,8 & 9) to track risks over the project life cycle.
If no update has been done for some time, then the intermediate weeks should be filled with the previous REI figure (you should correct the week numbers according to the project timescale as you make the first plan).
The graph will update automatically, but if you change the number of weeks the project runs for, you will need to manually adjust the 'source data' of the chart to use the correct data range.
Examples of Risk Categories
Types | Examples | Ownership
Technology/Manufacturing Risks | Top risks listed in Technology risk assessment and quick-scan that affects schedule/performance/ Cost/ power | Respective Leads
Program/Project Mgt. Risks | > Risk of not meeting timeline- eg: some team dependencies not clear, or plan not in detail or not visible | Project Manager
> Budget
> Late unplanned changes
Organizational Risks | > Anything related to resource/ resource competence | Technical/ Functional/ Design leads or Resource Managers
> cost cutting, program priority and team reassignment
> Risks due to teams not released from other program/ project on time
> new team ramp up/ missing effort estimation
Extrnl Risks (mrkt/suppliers/contractors) | Mrkt: risk due to market dynamics, Competition, Customer design win targets not meeting | for Mrkt- Product marketers
| Mrkt: Risk due to customer samples/ product release don't meet the customer target | for Supplier/Contractors- Either PM or resource managers
Suppliers : Supplier capabilities influencing commitment
Contractors: Contractors capabilities influencing commitment
Commercial Risks | > product cost increase or Margin challenges to meet market demand | Product Marketers
>Technical items risks business for not meeting Performance/ features/ power/ SW / Boards/ Package etc
Technical/Quality/Performance Risks | Top risks listed in D-FEMA or QRS that affects schedule/performance/ Cost/ power | Architects/ Technical / Functional / Design leads
Safety & compliance risks | Risks related to e.g. Functional Safety requirements, Risks related to being compliant with applicable standards, like automotive and security standards” | Technical/ Functional/ Design Leads

## Ranking Guide Risk Register
Ranking Guidelines Risk register for Project Risks
Impact (I)
Rank | Description: Impact - on Project | Examples, Criteria | For comparison: Severity / Impact - automotive scale
1 | No effect | No impact expected | No effect
2 | Very minor | Achievable within projects normal targets | Very Minor, Fit & Finish/Squeak & Rattle item does not conform. Defect noticed by discriminating customer
3 | Minor | Achievable well within exception criteria | Minor, Fit & Finish/Squeak & Rattle item does not conform. Defect noticed by average customer
4 | Low | Solution takes project close to exception criteria | Very Low, Fit & Finish/Squeak & Rattle item does not conform. Defect noticed by most customers
5 | Moderate | Unable to achieve an acceptable solution within exception criteria for next gate | Low, Vehicle/item operable, but Comfort/Convenience item(s) operable at reduced level of performance. Customer experiences some dissatisfaction
6 | Significant | R gate delay exceeds exception limits | Moderate, Vehicle/item operable, but Comfort/Convenience item(s) inoperable. Customer experiences discomfort
7 | High | Unable to meet current customer commitments | High, Vehicle/item operable, but at reduced level of performance. Customer dissatisfied
8 | Very high | Loss of business opportunities due to late release of product | Very High, Vehicle/item inoperable with loss of primary function
9 | Extremely high | Loss of significant business and/or reputation | Hazardous - with warning, Very high severity ranking when a potential failure mode affects safe vehicle operation and/or involves noncompliance with government regulation with warning
10 | Hazardous | Problem for project team's safety | Hazardous - without warning, Very high severity ranking when a potential failure mode affects safe vehicle operation and/or involves noncompliance with government regulation without warning
Probability (P)
Rank | Description: Probability of Occurence of Project risk | Examples, Criteria
1 | Rare | < 10% | Teams often find it easy to estimate this as percentages (20% likely to happen, or 80% likely), using this technique helps produce the appropriate rating. For example, if the estimate is 40% likely then the rating is 4.
2 |  | 10 - 20%
3 | Unlikely | 20 - 30%
4 |  | 30 - 40%
5 | Possible | 40 - 50%
6 |  | 50 - 60%
7 | Likely | 60 - 70%
8 |  | 70 - 80%
9 | Almost certain | 80 - 90%
10 |  | 90 - 100%

## Risk Review Records
Review Date | Attendees | Roles | Comments | Guideline on Project Risk review participation
By default the members of the project core team should be involved.
Further disciplines to be considereD: (if not already represented via the core team)
|  |  |  | Discipline | needed persons
Product Management
Architecture
Marketing
Partnership Management
Program Management
Security Manager
Export Control
Supply Chain Management
Quality Systems
PQE NPI
Product Engineer
Note on C2: Initials will suffice or meeting title if reviewed at say a Core team Meeting
Note on D2: provide the attendees roles as related to the project
Note on E2: Enter any comments relevant to the review, e.g. special occasions like gates
Note on G8: add further disciplines as needed
Note on H8: fill in names or initials

## Risk Register Form
| Risk Register for: | STRX ONECHIP RFE SW | Project Start: | <Date> |  |  | Last modified date: | 2023-08-21
| Document Owner: | Samrat Guha Niyogi | Start of Risk Management: | 2023-08-21 |  |  | Revision: | <2>
[5 empty] | Initial | [8 empty] | Updated
| Enter new Items in BLUE text. |  | Enter critical items in RED text. |  | assessment |  | 442 |  | REI = Risk Exposure Index (calculated as Probability x Impact) |  |  |  |  | assessment |  | 0
ID | Cause | Description of Risk | Risk Category | Effect | Prob. | Impact | REI | Owner | Team/ Assignee | Defined Action | Progress Updates | Status | Target Date | Prob. | Impact | REI
1 | SW AS Update not complete for EAR | Linking for EAR not complete | Technical/Quality/Performance | Not aligned to EAR criteria | 4 | 3 | 12 | Sri Krishnan | RFE SW |  |  | Closed | Apr'23 |  |  | 0 | 12 | 8
2 | SW RS Update not complete for EAR | Linking for EAR not complete | Technical/Quality/Performance | Not aligned to EAR criteria | 4 | 3 | 12 | Sri Krishnan | RFE SW | trending to closure by Sep end | Linking issue due to tool | On hold | 29/09/2023 |  |  | 0 | 12 | 9
3 | Unit RS Update not complete for EAR | Changes not complete. | Technical/Quality/Performance | Not aligned to EAR criteria | 5 | 5 | 25 | Sri Krishnan | RFE SW | trending to closure by Sep end | Analog and Digital changes done, review ongoing. 2 Digital blocks pending | Open | 29/09/2023
4 | SW Detailed design Update not complete for EAR | Changes not complete. | Technical/Quality/Performance | Not aligned to EAR criteria | 8 | 8 | 64 | Sri Krishnan | RFE SW | Maturity of coverage to continue till Q1'24 |  | Open | 31/03/2024 |  |  | 0 | 64 | 1
5 | SW Traceability Matrix QT/UT/IT not adequete | Changes not complete. | Technical/Quality/Performance | Not aligned to EAR criteria | 8 | 8 | 64 | Samrat | RFE SW | IT and UT traceability tag alignmnent with Unit RS and AS by Q4'23 end, Maturity of coverage to continue till Q1'24 | QT traceabilty < 50%, IT traceability tags broken, UT traceability incomplete | Open | 31/03/2024 |  |  | 0 | 64 | 2
6 | SW Test Specification not adequete | Coverage enhancement needed in Test Specification | Technical/Quality/Performance | Not aligned to EAR criteria | 5 | 5 | 25 | Dalton | RFE SW | Maturity of coverage to continue till Q1'24 |  | Open | 31/03/2024 |  |  | 0 | 25 | 7
7 | IP Val and SysVal feedback incorporation in RFE SW | code modification impacting performance | Technical/Quality/Performance | Pull in of deliverables not possible | 8 | 8 | 64 | Samrat | RFE SW | customer to be communicated |  | New | 31/03/2025 |  |  | 0 | 64 | 3
8 | Quality KPIs incorporations till PRC in RFE SW | code modification impacting code freeze | Safety and Compliance Risks | Pull in of deliverables not possible | 8 | 8 | 64 | Samrat | RFE SW | branching strategy for Denso and generic customer |  | New | 31/03/2026 |  |  | 0 | 64 | 4
9 | Fusa compliancy in RFE SW | code modification impacting code freeze | Safety and Compliance Risks | Pull in of deliverables not possible | 6 | 8 | 48 | Samrat | RFE SW | branching strategy for Denso and generic customer |  | New | 31/03/2027 |  |  | 0 | 48 | 6
10 | ASPICE compliancy in RFE SW | code modification impacting code freeze | Safety and Compliance Risks | Pull in of deliverables not possible | 8 | 8 | 64 | Samrat | RFE SW | branching strategy for Denso and generic customer |  | New | 31/03/2028 |  |  | 0 | 64 | 5
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
[7 empty] | 0 | [8 empty] | 0 | 0
Note on I5: Not to be changed after initial risk assessment
Note on B6: The ID should be unique for each risk
Note on C6: What causes the risk? Determining the Cause and the Effect of the risk will help in selecting Action and Owner.
Note on D6: Description of the risk to the NPI program
Note on E6: Select from the drop-down
Note on F6: What is the Effect of the risk? Determining the Cause and Effect of risk will help in selecting Action and Owner
Note on G6: Probability (1 to 10), 10 being most probable
Note on H6: Impact (1-10): 10 = very high 1 = very low
Note on I6: 1 is lowest 100 is highest Automatically calculated
Note on J6: The owner assigned is from the Project Core Team
Note on K6: Which team is dealing with risk? DRI can be outside the Core Team
Note on L6: Describe how the risk will be handled. Consider Mitigation action (preventative) first and Contingency (backup plan)
Note on M6: Update the progress of the action including actual dates.
Note on N6: Select from Dropdown: - New: action just entered - Open: action not started - Started: action started - On hold: temporarily onhold - Canceled: action cancelled - Closed: action finalized
Note on O6: Target date does not change. Use Progress Update to give details/dates of action (Date format only)
Note on P6: Probability (1 to 10), 10 being most probable
Note on Q6: Impact (1-10): 10 = very high 1 = very low
Note on R6: 1 is lowest 100 is highest Automatically calculated

## Risk Trend
#risks per zone |  |  | Top 3 risks |  |  |  |  | Frequency: | Monthly |  |  | Start Date: | 2023-08-21
Threshold | #Risks |  | Rank | ID | REI | Risk | Cause
> 39 | 6 | 4 | 1 | 4 | 64 | Changes not complete. | SW Detailed design Update not complete for EAR | Period | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
20 ... 39 | 2 | 5 | 2 | 5 | 64 | Changes not complete. | SW Traceability Matrix QT/UT/IT not adequete | week/month-nr. | 2023-08 | 2023-09 | 2023-10 | 2023-11 | 2023-12 | 2024-01 | 2024-02 | 2024-03 | 2024-04 | 2024-05 | 2024-06 | 2024-07 | 2024-08 | 2024-09 | 2024-10 | 2024-11 | 2024-12 | 2025-01 | 2025-02 | 2025-03 | 2025-04 | 2025-05 | 2025-06 | 2025-07 | 2025-08 | 2025-09 | 2025-10 | 2025-11 | 2025-12 | 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08 | 2026-09 | 2026-10 | 2026-11 | 2026-12 | 2027-01 | 2027-02 | 2027-03 | 2027-04 | 2027-05 | 2027-06 | 2027-07 | 2027-08 | 2027-09 | 2027-10 | 2027-11
< 20 | 2 | 7 | 3 | 7 | 64 | code modification impacting performance | IP Val and SysVal feedback incorporation in RFE SW | #RED
REI | 0 | [6 empty] | #YELLOW
|  |  |  | Please transcribe these values into table at the right |  |  |  | #GREEN
Risk Exposure (REI)
Mitigation Index (Progress)
|  |  | Number of actions defined: | 9
|  |  | Number of actions closed: | 1
|  |  | Mitigation Progress: | 11.11%
8
Note on L2: Choose Time Scale for Risk Management: Project teams should review and update risks in Risk Register on a regular basis Guideline for frequency (not mandatory): - If Project lifetime < 1 year: weekly / bi-weekly - If Project lifetime < 2 years: bi-weekly / monthly - If Project lifetime > 2 years: monthly Time Scale is automatically generated.
Note on P2: Start Date taken over from Risk Register Form.

## Validation
Risk Category | Status | Risk Sources | Review Frequency
Technology/Manufacturing | New | Business case viability | Weekly
Program Management | Open | Complex project setup | Bi-weekly
Project Management | Started | Contractual penalties agreed with (Key) customer(s) | Monthly
Organizational | On hold | Cost or funding issues
External (marketing/suppliers/contractors) | Canceled | Dependency on other project(s)
Commercial | Closed | Disruptions to continuity of operations
Technical/Quality/Performance |  | Hidden objectives
Safety and Compliance Risks |  | Inadequate communication with actual/potential customers or representatives
Inadequate staffing
Infeasible design
Insufficient coverage of prototype/test
Multi-site project
Open source software
Other
Patent issues
Poorly defined objectives
Required skills and competencies missing in Project Team
Team with little domain experience/knowledge
Unavailable technology
Uncertain or inadequate subcontractor/vendor capability
Uncertain requirements
Unpredicted effort - estimates unavailable/inadequate
Unrealistic schedule estimates or allocation

## Revision History
Revision History
Date | Author | Reviewers | Details of the change | Owner | Status
14/3/2023 | Samrat Guha Niyogi | Sri Krishnan; Sidda | Created draft version for EAR1.5 | Samrat Guha Niyogi
21/8/2023 | Samrat Guha Niyogi | Sri Krishnan; Sidda | Updated for EAR1.8 | Samrat Guha Niyogi