## Template info (hidden)
| Scope |  |  | The purpose of this template is to help to define the assessment plan.
Template information
Document name | Version | Author | Comments / Changes |  | Approver | Date | Status
Assessment_Plan_Template | 1 | Eric Guillen | Creation of a template for the planning of Confirmation measures in agreement with Bcam 7. |  | NA | 2017-03-11 | Obsolete
Assessment_Plan_Template | 2 | Eric Guillen | Remove ASIL reference for the confirmation measures according to TUV SUD findings avoiding any confusion. |  | NA | 2017-08-18 | Obsolete
Auto Functional Safety Assessment Plan template | 3 | Coco Gubbels | Updated lifecycle with BCaM 7 v1.2 (PC = Major Milestone, not Phase Gate) and name change in order to align with other BCaM7 templates |  | NA | 2017-11-28 | Obsolete
Automotive Safety Assessment Plan template | 4 | Eric Guillen | -Template updated following new requirements of ISO 26262:2018 (new CRs for Impact analysis and technical Safety Concept, remove CR software tool evaluation) |  | Core team (Core team: Franck Galtie, Valerie Bernon, Ludovic Rota, Erik Santiago, Rolf Schagenschaft, Simona Almajan) | 2019-04-01 | Obsolete
Automotive Safety Assessment Plan template | 5 | Erik Santiago | updated according to collabnet improvement ticket artf700064 |  | Anamaria Hutuelac | 2019-04-02 | Released
Remark
Status can be: - Obsolete - Draft - Released

## Document info
| Scope |  |  | The purpose of this document is to define the planning of Confirmation Measures at HW and SW level.
Document information
Document name | Version | Author | Comments / Changes |  | Approver (Functional safety assessor) | Date | Status
Safety_Assessment_Plan_STRX RFE FW | 1 | Sandeep | Initial place holder |  |  | 2020-11-30 | Draft
Safety_Assessment_Plan_STRX RFE FW | 2 | Sandeep | Updates: - Change of Planning for EAR AUDIT & ASSESSMENT to JAN 2022 end instead of April. The updates are aligned with STRX- PM(Sushil), RFE PM(Maulik), RFE ARCH (Artur) and Assessor ( Mathieu) |  | Mathieu Tajan | 2021-04-26 | Approved
Safety_Assessment_Plan_STRX RFE FW | 3 | Rashmi | Updates: - Change of Planning for EAR AUDIT & ASSESSMENT to Dec 2022 instead of Feb 2022 cause EAR 1.5 will be release for the design assessment. The updates are aligned with STRX- PM(Sushil), RFE PM(Maulik), and Assessor ( Mathieu) |  | Mathieu Tajan | 2022-05-17 | Approved
Safety_Assessment_Plan_STRX RFE FW | 4 | Rashmi | Impact Analysis made as applicable based on discussionwith the assessor and FS Architect |  | Mathieu Tajan | 2022-06-21
Safety_Assessment_Plan_STRX RFE FW | 5 | Rashmi | Updated the dates for other assessments - Safety analysis, Safety Audit and release assessment |  | Mathieu Tajan | 2023-06-27
Remark
Document shall be saved as: Safety_Assessment_Plan_xxxxxx xxxx is the project name Or according to the name defined in the documentation management plan.
Status can be: - Obsolete - Draft - Released
Hide "Template info" tab when creating the document
Depending on ASIL and type of development (HW or SW) remove the non useful cells

## Assessment Plan
Project
|  | Project name | STRX RFE FW
|  | ASIL targeted | ASIL B
|  | Lead Assessor | Anamaria Marilena Hutuleac <anamaria.hutuleac@nxp.com> Mathieu Tjan (mathieu.tjan@nxp.com)
|  | BCaM7 HW | [PI] | [PCA] | [PDA] | [PPA] | TO | CES | RQ | CQS | [R] | E | [PC]
|  | BCaM7 SW | [PI] | [PCA] | [PDA] | [PPA] |  | EAR | PRC | RFP | [R] | E | [PC]
Project Target Dates
Activity | Confirmation measures type | Gate / Milestones | [11 empty] | Assessor / Role / Ix
NPI | Confirmation Review of the Impact Analysis | PCA |  | NA
SW | Confirmation Review of the Impact Analysis | PCA | [5 empty] | 2022-06-30
NPI, SW | Confirmation Review of the Technical Safety Concept | PPA |  |  |  | 2020-12-18 | [7 empty] | Anamaria Marilena Hutuleac <anamaria.hutuleac@nxp.com> / SW Mathieu T
NPI, SW | Confirmation Review of the Safety Plan | PPA |  |  |  | 2020-12-18 | [7 empty] | Anamaria Marilena Hutuleac <anamaria.hutuleac@nxp.com>/ SW
NPI | Confirmation Review of the Safety Analysis | TO |  |  |  |  | x | [6 empty] | Andres Barrilado <andres.barrilado_2@nxp.com> (HW) Anamaria Marilena Hutuleac <anamaria.hutuleac@nxp.com> (SW)
SW | Confirmation Review of the Safety Analysis | EAR | [5 empty] | 2023-09-29 | [5 empty] | Anamaria Marilena Hutuleac <anamaria.hutuleac@nxp.com>/ SW
NPI | Confirmation Review of the Safety case | [R] | [8 empty] | x |  |  | Andres Barrilado <andres.barrilado_2@nxp.com> (HW) Anamaria Marilena Hutuleac <anamaria.hutuleac@nxp.com> (SW)
SW | Confirmation Review of the Safety case | RFP | [7 empty] | 2024-05-15 |  |  |  | Anamaria Marilena Hutuleac <anamaria.hutuleac@nxp.com>/ SW
NPI, SW
NPI | FS Design assessment | TO |  |  |  |  | x | [6 empty] | Andres Barrilado <andres.barrilado_2@nxp.com> (HW) Anamaria Marilena Hutuleac <anamaria.hutuleac@nxp.com> (SW)
SW | FS Design assessment | EAR | [11 empty] | Anamaria Marilena Hutuleac <anamaria.hutuleac@nxp.com>/ SW
NPI | FS Release Assessment | [R] | [8 empty] | x |  |  | Andres Barrilado <andres.barrilado_2@nxp.com> (HW) Anamaria Marilena Hutuleac <anamaria.hutuleac@nxp.com> (SW)
SW | FS Release Assessment | RFP | [7 empty] | 2024-05-15 |  |  |  | Anamaria Marilena Hutuleac <anamaria.hutuleac@nxp.com>/ SW
NPI, SW
NPI | Safety Audit: | [R] | [8 empty] | x |  |  | Andres Barrilado <andres.barrilado_2@nxp.com> (HW) Anamaria Marilena Hutuleac <anamaria.hutuleac@nxp.com> (SW)
SW | Safety Audit: | RFP | [7 empty] | 2024-05-15 |  |  |  | Anamaria Marilena Hutuleac <anamaria.hutuleac@nxp.com>/ SW
Concept
Definition
Planning
Execution
Closure
NPI LIFECYCLE
PDA
R
PCA
PI
PPA
TO
CES
RQ
E
CQS
BCaM7.0 Project Life Cycle
EAR
PRC
RPF
HW
SW
Note on L35: Rashmi K C: EAR 1.5 will be release with FS implemented - Hence assessment will be targetted for EAR 1.5 than EAR 1.4
Note on L40: Rashmi K C: EAR 1.5 will be release with FS implemented - Hence assessment will be targetted for EAR 1.5 than EAR 1.4